## Summary
Multi-Tenant Auth App — Validation Report (Phase 3)
Scope: Super-admin session. Master Data + Auth. Tenant-side authorization & security chains: NOT yet executed (see Security sheet).
Result counts (live from Test Cases sheet)
Status | Count
PASS | 36
PASS* (partial) | 37
DEFECT / FAIL | 5
PENDING | 0
TOTAL executed | 42
Defects summary
ID | Area | Severity | Issue
F-5 | Master Data grid (DataTable) | High | Null reference value crashes whole grid (typeof null==='object' then value.Lat); no error boundary.
F-1 | paymentBreakups create | High | POST with all valid FKs -> 500 Internal Server Error (create broken).
F-2 | branchUserGroupMappers | High | FE free-text UserGroupId vs BE GUID (400); valid GUID -> 500 (FK violation unhandled).
F-3 | addressDetails/branchDetails +peers | Medium | Missing DB-required FK -> 500 instead of 400.
F-4 | Inline + reference component | Low | Newly inline-created record not auto-selected in dropdown (UX).

## Test Cases
ID | Category | Module | Test Case (Description) | Steps | Expected Result | Actual Result | Status | Severity
TC-A01 | Auth | Login | App reachability | 1) Open http://localhost:3000/login 2) GET http://localhost:3001/ | Login page renders w/ Google button; backend root 200 | Both load; backend 200 | PASS | -
TC-A02 | Auth | API | Unauthenticated API rejected | 1) Call GET /api/admin/users and /api/taxtypes with no token | 401 Unauthorized | Both 401 | PASS | -
TC-A03 | Auth | Login | Super-admin Google login | 1) Click Sign in with Google 2) Complete Google auth 3) Decode app_token cookie | Redirect to /dashboard; JWT has tid, TENANT:SUPER_ADMIN, role SUPER_ADMIN | Logged in; scopes/roles correct; TTL 60m | PASS | -
TC-A04 | Auth | API | Super-admin privileged endpoints | 1) GET /api/data/settings, /api/reports, /api/reports/billing, /api/audit/logs | 200 (super-admin bypass) | All 200 | PASS | -
TC-A05 | Auth | Session | Session expiry | 1) Wait ~60 min for token TTL | App returns to /login | Confirmed expiry to /login | PASS | -
TC-B01 | Access | Approvals | IAM Approvals renders | 1) Open /admin/approvals | Renders; empty state | Renders ('No onboarding requests') | PASS | -
TC-B02 | Access | Users | IAM Users renders | 1) Open /admin/users | Lists users w/ status/roles/flags | Both accounts listed correctly | PASS | -
TC-B03 | Access | Roles | IAM Roles renders | 1) Open /admin/roles | Lists roles; system roles protected | System roles show no Edit/Delete | PASS | -
TC-B04 | Access | Features | IAM Features renders | 1) Open /admin/features | Lists features w/ scope+category | Renders correctly | PASS | -
TC-B05 | Access | API | Admin API baseline | 1) GET onboarding/users/roles/features | 200 + data | All 200 | PASS | -
TC-C01 | Master Data | (all) | Master Data index renders | 1) Open /master | 6 categories + module cards | Renders all | PASS | -
TC-C02 | Master Data | Tax Types | List view | 1) Open /master/taxTypes | Rows, sortable headers, pagination footer | Renders correctly | PASS | -
TC-C03 | Master Data | (all) | Empty state | 1) Open module with no records / search miss | 'No Records Found' | Correct empty state | PASS | -
TC-C04 | Master Data | Tax Types | Search filter | 1) Type 'zzz-no-match' in search | Filtered; empty state | Empty state shown | PASS | -
TC-C05 | Master Data | Tax Types | Create: empty required fields | 1) Add 2) leave Name+Value blank 3) Create | Inline required errors; blocked | 'Name/Value is required' | PASS | -
TC-C06 | Master Data | Tax Types | Create: value>max (client) | 1) Value=150 (max 100) 2) Create | Blocked client-side | 'Value must be <=100' | PASS | -
TC-C07 | Master Data | Tax Types | Create: happy path | 1) Name 'QA Test VAT', Value 18 2) Create | Success toast + row | 'Record created successfully' | PASS | -
TC-C08 | Master Data | Tax Types | Update | 1) Edit row 2) Value 18->22 3) Update | Success toast; value updated | 'Record updated successfully' | PASS | -
TC-C09 | Master Data | Tax Types | Delete + confirm | 1) Delete 2) Confirm dialog | Row removed after confirm | 'Record deleted successfully' | PASS | -
TC-D01 | Master Data | API | Server rejects out-of-range | 1) POST /api/taxtypes {Value:150} | 400 validation | 400 'must be <=100' | PASS | -
TC-D02 | Master Data | API | Server rejects missing field | 1) POST {Value:5} (no Name) | 400 | 400 'Name is required' | PASS | -
TC-D03 | Master Data | API | Forged TenantId rejected | 1) POST {Name,Value,TenantId:other} | 400; no cross-tenant write | 400 (unknown field rejected) | PASS | -
TC-D04 | Master Data | API | Invalid id param | 1) GET /api/taxtypes/not-a-real-id | 400 | 400 (UUID validation) | PASS | -
TC-D05 | Master Data | API | Unique constraint | 1) POST duplicate StartCounterNo / Lat | 409 | 409 'already exists' | PASS | -
TC-E01 | All 6 categories | (31 modules) | All-module CREATE sweep | 1) Authenticated POST one record per module (FK graph built bottom-up) | All create 201 | 29/31 -> 201 (2 defects: F-1,F-2) | PASS* | -
TC-E02 | All 6 categories | (21+ modules) | All-module LIST endpoints | 1) GET /api/{module} for all modules | 200, tenant-scoped | All 200 | PASS | -
TC-F01 | Master Data | Tax Types | FK dependency dropdowns present | 1) Open Item Details create | Category/UOM/CostInfo selects w/ inline + | Present | PASS | -
TC-RI1 | All FK modules | (6 relations) | Delete parent that is referenced | 1) Create parent 2) reference in child 3) delete parent | Blocked gracefully; child not orphaned | 409 'Cannot delete - referenced' | PASS | -
TC-RI2 | All FK modules | (5 relations) | Update parent propagates to child | 1) Create parent+child 2) update parent value 3) re-read child joined view | Child joined field reflects new value | Propagates (live JOIN) | PASS | -
TC-RI3 | Master Data | Tax Group Mapper | Inline + nested-create end-to-end | 1) Add mapper 2) '+' Tax Group 3) create inline 4) select+submit | Nested modal stacks; created; usable in child | Works; mapper created w/ inline TG | PASS | -
TC-UI1 | Master Data | Categories | Full UI CRUD | 1) Create 2) Edit name 3) Delete+confirm | All succeed w/ toasts | All PASS | PASS | -
TC-UI3 | Master Data | Units of Measure | Full UI CRUD incl. boolean | 1) Create 2) Edit toggling Is Primary (real click) 3) Delete | All succeed; IsPrimary persists 0->1 | All PASS | PASS | -
TC-UI5a | Master Data | (all) | Column sort asc/desc | 1) Click NAME header twice | Ascending then descending w/ arrows | Sorts both ways | PASS | -
TC-UI5b | Master Data | (all) | Refresh button | 1) Click Refresh | Reloads list, no error | Works | PASS | -
TC-UI5c | Master Data | Tax Group Mapper | Pagination | 1) 11 records 2) click page 2 | Prev/1/2/Next; page 2 shows record 11 | 'Showing 11 to 11 of 11' | PASS | -
TC-G01 | Reports | Reports | Reports page renders (super admin) | 1) Open /reports | Renders (bypass) | Renders; API 200 | PASS | -
TC-G02 | Audit | Audit | Audit visibility (super admin) | 1) Open /audit | All logs visible; own actions logged | 141 logs; full visibility | PASS | -
TC-F1 | Payments | paymentBreakups | Create returns 500 | 1) POST /api/paymentbreakups w/ all valid FKs | 201 created | 500 Internal Server Error (reproduced x2) | DEFECT | High
TC-F2 | Organization | branchUserGroupMappers | FE/BE contract + FK 500 | 1) POST UserGroupId as text 2) as valid GUID | 201 or clean 400 | text->400 'must be GUID'; valid GUID->500 | DEFECT | High
TC-F3 | Contacts/Org | addressDetails, branchDetails | 500 instead of 400 on missing FK | 1) POST omitting a DB-required FK | 400 validation message | 500 Internal Server Error | DEFECT | Medium
TC-F4 | Master Data | (all reference forms) | Inline + does not auto-select | 1) '+' create parent inline 2) observe dropdown | New record auto-selected | Not auto-selected (option present, manual pick) | DEFECT | Low
TC-F5 | Master Data | GenericCrudPage/DataTable | Grid white-screens on null reference | 1) Open a grid w/ a record having null reference (e.g. /master/itemDetails) | Cell renders gracefully | Uncaught TypeError 'Cannot read null.Lat'; whole page crashes (no error boundary) | DEFECT | High

## Module Coverage
Category | Module | Create | List | Update | Delete | Validation | Del-if-Referenced | Update-Propagation | Inline +
Master Data | taxTypes | UI | Y | UI | UI | Y | parent | Y | -
Master Data | uom | UI | Y | UI | UI | - | Y | Y | -
Master Data | uomFactors | API | Y | - | - | - | child | child | -
Master Data | categories | UI | Y | UI | UI | - | Y | Y | +via mapper
Master Data | taxGroups | API | Y | API | - | - | Y | Y | UI (via mapper)
Master Data | taxGroupTaxTypeMappers | API/UI | Y | - | - | - | child | child | UI end-to-end
Master Data | accountTypeBases | API | Y | - | - | - | - | - | -
Organization | organizations | API | Y | API | - | - | - | - | -
Organization | branchDetails | API | Y | - | - | 500-missing-FK | - | - | -
Organization | branchUserGroupMappers | DEFECT | Y | - | - | - | - | - | -
Transactions | transactionTypes | API | Y | - | - | - | - | - | -
Transactions | transactionTypeConfigs | API | Y | - | - | 409 unique | - | - | -
Transactions | transactionTypeStatuses | API | Y | - | - | - | - | - | -
Transactions | transactionTypeBaseConversions | API | Y | - | - | - | - | - | -
Transactions | transactionTypeConversionMappers | API | Y | - | - | - | - | - | -
Transactions | transactionDetailLogs | API | Y | - | - | - | - | - | -
Transactions | transactionItemDetails | API | Y | - | - | - | - | - | -
Inventory | itemDetails | API | Y | - | - | - | child | child | form seen; grid crash F-5
Inventory | batchDetails | API | Y | - | - | - | - | - | -
Inventory | costInfos | API | Y | - | - | - | - | parent | -
Contacts | contactAddressTypes | API | Y | - | - | - | Y | - | -
Contacts | contactDetails | API | Y | - | - | - | child | - | -
Contacts | addressDetails | API | Y | - | - | 500-missing-FK | - | - | -
Contacts | locationDetails | API | Y | - | - | 409 unique | - | - | -
Contacts | mapProviders | API | Y | - | - | - | Y | Y | -
Contacts | mapProviderLocationMappers | API | Y | - | - | - | child | child | -
Payments | paymentReceivedTypes | API | Y | - | - | - | - | - | -
Payments | paymentModes | API | Y | - | - | - | - | - | -
Payments | paymentModeTransactionDetails | API | Y | - | - | - | - | - | -
Payments | paymentDetails | API | Y | - | - | - | - | - | -
Payments | paymentBreakups | DEFECT (500) | Y | - | - | - | - | - | -

## Security Findings
Security / Authorization Findings
These are code-analysis risks (Phase 1). Dynamic execution requires the TENANT account session and is NOT yet done — status PENDING.
ID | Area | Risk / Hypothesis | Planned test | Severity | Status
S-1 | Session invalidation | Suspending/deleting a user does NOT invalidate an existing JWT (stateless; logout returns 200 only). | Capture tenant JWT; SA suspends/deletes; replay tenant JWT vs /api/taxtypes. | High | PENDING
S-2 | Tenant isolation (IDOR) | GET /api/admin/roles/:roleId/permissions is not tenant-scoped (roleId only). | As tenant-admin A, request a roleId of tenant B. | High | PENDING
S-3 | Session expiry handling | Backend returns 403 for expired token, but client interceptor only handles 401 -> no auto-logout/redirect. | Expire token; observe app behavior on API 403. | Medium | PENDING
S-4 | Route guard | /audit route has NO client-side guard; reachable while logged out. | Visit /audit logged out; expect redirect to /login (won't). | Medium | PENDING
S-5 | Scope mismatch | FE scopes.js uses 'reports:READ' vs BE 'REPORTS:READ' -> guard/server may disagree. | As tenant with reports role, open /reports; compare FE guard vs API. | Low | PENDING
S-6 | Token exp ignored | decodeToken ignores exp; UI looks logged-in with expired token until an API call fails. | Load app with expired cookie; observe. | Low | PENDING
C-neg | Authorization boundary | As TENANT, every super-admin-only action via (1) UI (2) direct URL (3) API replay must 401/403. | Run all 3 vectors against /api/admin/*, data/settings, audit cross-tenant. | High | PENDING
D-iso | Tenant isolation | Confirm one tenant cannot read/modify another's data (change IDs in URL/API). | Forged tenantId/foreign roleId; single-tenant env limits scope. | High | PENDING
B-dep | Super-admin->tenant lifecycle | SA edit/suspend/delete tenant propagates (tenant loses access on next login; refs handled). | Full chain via UI + JWT replay. | High | PENDING
E-goog | Google integration | OAuth connect/consent, token storage, disconnect/revoke, cancel/deny/error paths. | Both accounts; cancel/deny popup. | Medium | PENDING